## Edition 5 Volume 2
v.3.0:20230810
Volume, Section, Chapter | Author | Comments | Current Status | Expected Receiving Date | Progress October 2024
Volume 2: Risk assessment (hazard identification, probability analysis, consequence analysis) and its purposes, the methodology and its limitations | Hans Pasman
Assess & TOC | Hans Pasman | "to be synchronized with Vol.1"means Vol. 1 writes a summary and refers to Vol.2, and in Vol. 2 the importance for Vol.1 will be mentioned.
First Draft | Hans Pasman | "Vol.1 - Vol.2 split to be decided" is clear.
Final | Hans Pasman | "To Vol.1" means just moving the chapter to Vol.1.
Part 2A: Why risk assessment and what is required for it?
Chap 2A.1: Process safety, hazard and risk |  | To be synchronized with Vol. 1
1: Historical prologue; why and when risk assessment and management | Hans Pasman | To be synchronized with Vol. 1 |  |  | Draft completed
2: Hazard and risk definitions | Hans Pasman | To be synchronized with Vol. 1 |  |  | Draft completed
3: Safety triad concept | Hans Pasman | To be synchronized with Vol. 1 |  |  | Draft completed
4: Safety science, Safety-I, -II, -III, Safety Differently, and Effects on Risk assessment | Hans Pasman | To be synchronized with Vol. 1 |  |  | Draft completed
5: Risk assessment methodology, general introduction | Hans Pasman | To be synchronized with Vol. 1 |  |  | Draft completed
6: Socio-technical system approach | Hans Pasman | To be synchronized with Vol. 1 |  |  | Draft completed
7: Effects of big data and analytics on risk assessment | Md Tanjin Amin | To be synchronized with Vol. 1 |  |  | Draft completed
8: Risk communication (see also 2D.6.5) | Howard Pike | To be synchronized with Vol. 1 | First draft promised | 2024-12-01 | The author is in contact.
Chap 2A.2: Overview of new concepts and methods in safety and security risk assessment process
1: The contribution of system resilience in minimizing losses, an introduction | Hans Pasman | To be synchronized with Vol. 1 |  |  | Draft completed
2: Security Assessment Elements: Physical and Cyber | Tanjin and El-Kady; David Moore | To be synchronized with Vol. 1 |  |  | Draft completed
3: UNCERTAINTY CHARACTERIZATION (BAYESIAN NETWORK APPLICATIONS, see 2C.4) |  |  |  |  | As of December 2023, Zaid's part is missing.
1 Uncertainty in Risk Assessment (definitions, types, sources | Zaid Kamil
2 Probability theory (Frequentist and Bayesian inference) | Zaid Kamil
3. Dempster-Shafer theory of evidence | Zaid Kamil
4. Fuzzy Sets and Logic, Applications | Long Ding, Jie Ji
5. Cloud model and Set Pair Analysis | Zaid Kamil
6. Interval Analysis | Zaid Kamil
4: Statistical and machine learning (ML and AI) data processing techniques for risk assessment | Kamil,Alauddin |  |  |  | Draft completed
Chap 2A.3: Hazard identification and characterization
1: Properties of materials |  | To be synchronized with Vol. 1 | Author Assigned
1. General property data sources, tests and criteria, storage and transport regulation | Maria Papadaki, Hans Pasman | To be synchronized with Vol. 1 | Author Assigned |  | Will be end of 2024
2. Reactive chemicals | Robert Bellair, Pranav Bhagaria | To be synchronized with Vol. 1 | Author Assigned |  | Draft completed
3. Hydrogen properties; materials compatibility | Prakash Kamathuru Andrzej Pekalski? | To be synchronized with Vol. 1 | Author Assigned |  | LNG Is first, H2 will be later
4. Ammonia Hazards
Scenarios
2: Accident cause structures, investigation tools | Hans Pasman | To be synchronized with Vol. 3 | First draft complete |  | This is a worryless one!
3, HAZID methods PHA, HAZOP, FMEA, system approach STPA | Mike Stone?; Dr.Jack Chosnek: | To be synchronized with Vol. 1
4: Accident databases, search strategies | Combine with 2 |  | Author Assigned |  |  | Please find another author (December 2023)
5: Scenario definition and representation | Combine with 3 | Vol.1 - Vol.2 split to be decided | Author Assigned |  |  | Please find another author (December 2023)
6: Critical considerations | Combine with 3 |  | Author Assigned
Part 2B: Consequence analysis | Scott Ostrowski
Chap 2B.1: Overview Consequence Analysis aspects | Hans Pasman | To be synchronized with Vol. 1 |  |  | Draft completed
Chap 2B.2: Source term, release characterization | Hans Pasman |  |  |  | Draft completed
Chap 2B.3: Gas/vapor and aerosol-cloud dispersion | Tom Spicer/ Savio Vianna |  |  | 2024-12-01 | Draft is being reviewed by Tom Spicer
Chap 2B.4: Fire | Long Ding; Jie Ji | Summary in Vol.1 |  |  | Drafts completed, figures copyright permissions are missing
1. Historical introduction
2.Basics/Concepts |  | To be synchronized with Vol. 1
3. Mechanisms (Including combustion, heat transfer, flow) |  | To be synchronized with Vol. 1
4. Ignition
5. Pool fires
6. Jet and engulfing fires
7. Vapor cloud flash fires
8. Fireballs
9. Fire risk
10. Fire prevention and mitigation
Chap 2B.5: Explosion types, (incl BLEVES): Explosion risk mechanisms and models, explosion risk | Kees van Wingerden | Summary in Vol.1 | Author Assigned | End of 2024 | New deadline for all these chapters is end 2024. Dr. Pasman knows the authors.
1: Historical introduction and basics | Kees van Wingerden | To be synchronized with Vol. 1 | Author Assigned | End of 2024
2: Premixed Combustion Is Combustion section in Fire sufficient? | Scott Davis |  | Author Assigned | End of 2024
3. Gas and vapor explosions - Confined and unconfined | Multiple authors |  | Author Assigned | End of 2024
1: Introduction and combustion phenomena | Kees van Wingerden/Elaine Oran |  | Author Assigned | End of 2024
2: Basic properties - Relevant physical properties | Kees van Wingerden |  | Author Assigned | End of 2024
3: Explosion prevention | Kees van Wingerden |  | Author Assigned | End of 2024
4: Explosion consequences and consequence reduction/mitigation | Multiple authors |  | Author Assigned | End of 2024
5: Confined explosions |  |  | Author Assigned | End of 2024
1: Gas and vapor explosions in vessels and rooms (confined) | Kees van Wingerden |  | Author Assigned | End of 2024
2: Mitigation gas and vapor explosions in vessels | Multiple authors |  | Author Assigned | End of 2024
1: Explosion venting | Gordon Andrews/ Roth Phylaktou |  | Author Assigned | End of 2024
2: Explosion suppression | Kees van Wingerden |  | Author Assigned | End of 2024
3: Containment | Greg Knight? |  | Author Assigned | End of 2024
4: Explosion absorbing systems | Kees van Wingerden |  | Author Assigned | End of 2024
3: Gas and vapor explosions in pipes | Kees van Wingerden/Elaine Oran |  | Author Assigned | End of 2024
4: Mitigation of gas and vapor explosions in pipes | Kees van Wingerden |  | Author Assigned | End of 2024
6: Unconfined explosions |  |  | Author Assigned | End of 2024
1: Gas and vapor explosions in process areas (unconfined) | Multiple authors; Cynthia Spitzenberger for risk assessment |  | Author Assigned | End of 2024
2: Accidents - DDT cases | Mike Johnson | To be synchronized with Vol. 3 | Author Assigned | End of 2024
3: Experimental research | Mike Johnson/Elaine Oran |  | Author Assigned | End of 2024
4: Modeling - software: CFD and BST etc | Kees van Wingerden / Elaine Oran |  | Author Assigned | End of 2024
1: PHAST, Safeti -- See 2D.1.2.1 | David Worthington |  | Author Assigned | End of 2024
2: EFFECTS, Riskcurves | Hans Boot, Sonia Ruiz Perez |  | Author Assigned | End of 2024
4: SafeSite, QRATool | Quentin Baker |  | Author Assigned | End of 2024
5: FRED, SHEPHERD | Steven Betteridge (TBC) |  | Author Assigned | End of 2024
6: FLACS | Djurre Siccama |  | Author Assigned | End of 2024
7: KFX/EXSIM | Evanger, Huser |  | Author Assigned | End of 2024
5: Mitigation | Mike Johnson |  | Author Assigned | End of 2024
6: Structural response | Robert Brewerton |  | Author Assigned | End of 2024
7: Aerosols | Kees van Wingerden |  | Author Assigned | End of 2024
8: Dust explosions | Robert Bellair |  | Author Assigned | End of 2024
9: Hybrid mixture explosions (dust and vapor) | Kees van Wingerden, Paul Amyotte |  | Author Assigned | End of 2024
4: BLEVEs | Delphine Laboureur |  | Author Assigned | End of 2024
5: Run-away, thermal runaway or thermal explosion - risks | Alex Kummer/ Tamas Varga | Coordinate with 2A.3.1.2 | Author Assigned | End of 2024
6: High explosives/Condensed phase explosion Shock wave/blast | Paul Cronin |  | Author Assigned | End of 2024
7: Deflagration. Gun powder. DDT | Hans Pasman |  | Author Assigned | End of 2024
8: Lithium battery Explosion and Fire |  |  |  | End of 2024
9: Vessel burst | Kees van Wingerden |  | Author Assigned | End of 2024
10: Rapid Phase Transition LNG | Kees van Wingerden |  | Author Assigned
11: Fragment hazards |  |  |  | End of 2024
Chap 2B.6: Natural hazards/NaTech and other threats by consequences of external accidents | Valerio Cozzani | To be synchronized with Vol. 1 | Author Assigned |  | Draft completed
Chap 2B.7: Escalation scenarios and Domino effects | Kamran Gholamizadeh MCPS Vol.5 + Storage tnks | To be synchronized with Vol. 1 | Author Assigned | End of 2024
Chap 2B.8.1 and 2: Cryogens Liquefied natural gas (LNG) and Hydrogen (LH2) | Bin Zhang LH2; Tomasz Olewski, Prakash Kamathuru, Whidayat LNG | Vol.1 - Vol.2 split to be decided | Author Assigned |  | LNG: Sep 2024 Tomasz started; Prakash and Whidayat will make outline. LH2 Bin Zhang writes with students.
Chap 2B.8.3 Supercritical and pressurized CO2 (transport and CCS) | Dr. Giuseppe Maschio. Dr. Chiara Vianello, Dr Paolo Mocellin | To be synchronized with Vol. 1 |  |  | This is a new chapter that has been added.
Chap 2B.9: Impact including injury, lethality, assets, environment, reputation, costs 1: Injury and lethality probits |  | To be synchronized with Vol. 1
2: Asset damage probits | Valerio Cozzani |  | Author Assigned |  | Chao Chen progress in literature? Asking him to write for Lees?
3: Structural damage due to blast | Robert Brewerton |  | Author Assigned |  | This chapter should move.
4: Environmental damage | Sadiq Saeed |  | Author Assigned |  | I do not expect him to write anything within a year.
5: Reputation damage | Hans Pasman |  |  |  | Dr. Pasman may tell.
6: Conversion into costs | Sunhwa Park |  |  |  | Dr. Pasman contacted Sunhwa and her colleague. They wanted to write. Last communication Aug.2024.
Chap 2B.10 Transportation |  | To be synchronized with Vol. 1
Chap 2B.10.1: Hazmat transportation risks | Kamran Ghozalizadeh | To be synchronized with Vol. 1 |  |  | Kamran has completed a draft.
Chap 2B.10.2 Hazmat Pipeline Transportation Risks, Introductory Reader Guidance | Hans Pasman | To be synchronized with Vol. 1 | Author Assigned |  | Almost completed
Chap 2B.10.3 Corrosion and Corrosion Management, incl. MIC hp | Susmitha Purnima Kotu | To be synchronized with Vol. 1 |  |  | Almost completed
Chap 2B.10.4 Hydrogen embrittlement | Nicola Paltrinieri, Antonio Alvaro | To be synchronized with Vol. 1 |  |  | Promised for end of 2024
Chap 2B.10.5 Condition assessment and risk management of aging subsea oil and gas pipelines corr. | Xinhong Li | To be synchronized with Vol. 1
Chap 2B.11: Special problems aging plants | Paolo Bragatto | Relocate Vol.1? |  | End of 2024 | Contact established Oct'24
Chap 2B.12: Multi-hazards, Combined effects, Case examples, Model comparisons, Risk accumulation | Combine with Escalation? |  |  |  | Another new chapter.
Part 2C: Chance event occurrence models and data
Chap 2C.1: Human, procedural, and organizational failures |  | To be synchronized with Vol. 1 | Author Assigned | 2023-06-01 | We have contacted multiple times; Nora wanted to write. December 2023: We will talk to Norafneeza.
Chap 2C.2: Event probability, equipment failure, reliability (engineering), unavailability | Katrina Groth; Ed. 4? OREDA HSE | To be synchronized with Vol. 1
Chap 2C.3: Expert elicitation methods | Esmaeil Zarei |  |  | 2024-02-01 | Draft completed
Chap 2C.4: Fault/Failure, and Event Trees, Bowtie, Cause-Effect Structures, Dependencies, Graphs, Bayesian Networks and Petri Nets | Pallavi Kumari/Hans Pasman | To be synchronized with Vol. 1 | Hans Pasman |  | Draft completed
Chap 2C.5: Inspection and maintenance, RBI - RCM - predictive maintenance | ????? | To Vol.1; Synchronize in Vol.2 |  |  | No author assigned.
Part 2D: RESULTING RISKS, MITIGATION, and DECISION-MAKING
Chap 2D.1: Risk determination
1: Methods, Tools, and Metrics for Effective Risk Analysis under Uncertainty | Kamran Gholamizadeh et al. | Refer 2.1 + 2.2 being in Vol.1 |  |  | Draft completed.
2: Risk determination software |  | To Vol.1 ?
1: DNV Phast-Safeti | David Worthington |  |  |  | Draft completed
2: Gexcon Effects-Riskcurves | Hans Boot |  |  | 2024-12-01 | No update as of now.
Chap 2D.2: Dynamic/operational risk assessment
1: Methods for different situations (batch reactors, continuous processes, plant, site) | Rajeevan Arunthavanathan | To be synchronized with Vol. 1 | Author Assigned | 2024-12-01 | No sign of doing anything. December 2023: We should aim for a different author.
2: Weak signals, early warnings, fault detection & diagnosis (FDD) | Rajeevan + Trish Kerin | To be synchronized with Vol. 1 | First draft in progress | 2024-12-01 | He did not provide any update for 8 months. Simple modification should have been complete the chapter long ago. December 2023: The draft was suvbmitted. Dr. Pasman gave some comments.
3: Simulation - gamification | Rajeevan Arunthavanathan |  | Author Assigned | 2024-12-01 | No sign of doing anything. December 2023: We should aim for a different author.
4. Emergency Management and Response, Simulation | Tanjin (Is this the best slot?) | Vol.1 - Vol.2 split to be decided | Author Assigned | 2024-12-01 | No sign of doing anything. December 2023: We should aim for a different author.
5: Offshore Risk Assessment and Risk Management | ?? Not sure about this | Vol.1 - Vol.2 split to be decided |  |  | This is to be added later.
Chap 2D.3: Cyber-physical security risks
1: Physical and cyber-security threats and attack scenarios | He Wen (Ahmed Elkady)/David Moore | Vol.1 - Vol.2 split to be decided |  |  | Draft completed
2: Game theory, Attacker-defender strength ratio | Ming Yang ?? |  | Author Assigned | 2024-12-01 | The best idea is to refer MCPS.
Chap 2D.4: Risk reducing measures (Will be much, if not all in Vol.1)
1: Hazard-barrier-target (H-B-T) models, bowtie, barrier types, layers of protection analysis (LOPA) | Alauddin | To Vol.1 | Author Assigned | 2024-12-01 | No sign of doing anything. December 2023: We should aim for a different author.
2: Safety management system | Alauddin | To Vol.1 | Author Assigned | ? | No sign of doing anything. December 2023: We should aim for a different author.
3: Human Factors/Ergonomics - Human System Interaction |  | Vol.1 - Vol.2 split to be decided | Author Assigned | ? | In one meeting, she was talking about these. But somehow distraction happened. We have requested for meeting by August. But no response.
4: Safety culture (incl. cyber security culture) - safety climate - organizational health | Dr. Stephanie Payne | To Vol.1 | Author Assigned | ? | Promised to complete/Oct'24 no response; Ivana Slovackova will contribute.
5: Physical Measures and barriers , Safety Instrumented System | Aracely Acevedo Jiyoti Sharma | To Vol.1 | Requested Aracely | 2024-12-01 | Jack talked to Aracely summer 2023. Jyoti was assigned in October 2023.
6: Inherently safer design principles in risk assessment - CISI | Alauddin | To Vol.1 | Author Assigned | 2024-12-01 | delayed
7: Alarm management, barrier health monitoring | Tanjin | Vol.1 - Vol.2 split to be decided | First draft complete. | 2024-12-01 | Nico reviewed. Stewart Behie has a look.
8: Security risk countermeasures ?????? | Pasman, Zaman, Luyang? | Vol.1 - Vol.2 split to be decided | Author Assigned | 2023-06-01 | Nothing produced. The first chapter needs to be completed.
9: Standards, codes and best practices |  | to Vol.1 | If needed, Dr. Pasman wanted to write
10: Procedures |  | Vol.1 - Vol.2 split to be decided | Author Assigned |  | In one meeting, she was talking about these. But somehow distraction happened. We have requested for meeting by August. But no response.
Chap 2D.5: Risk management and resilience
1: Physical asset management/risk register | Ming Yang | To Vol.1 | Author Assigned |  | Hans Pasman communicates with him
2: Resilience principles, required mechanisms, contingency planning | Ming Yang, Hans Pasman |  | Author Assigned |  | Draft completed
3: Resilience analysis, evaluation | Will be combined with 2D.5.2 |  |  |  | Draft completed
Chap 2D.6: Risk informed decision making
1: Validation of risk study; strength of evidence (SOE) or knowledge | Nazmul Rahmani/Hans Pasman |  | Author Assigned |  | Draft completed
2: Human Decision Making + Decision support methods | Yazdi | To be synchronized with Vol. 1 |  |  | Draft complted
3: Economic decision making | Sunhwa Park??? | To be synchronized with Vol. 1 | Author Assigned | 2024-12-01
4: Public risk acceptance | Howard Pike | To be synchronized with Vol. 1 | Author Assigned |  | Draft completed
Chap 2D.7: Risk assessment reporting requirements
1:quality of the process of QRA and decision making | Dr. Pasman | Literature available | Author Assigned |  | This chapter Dr. Pasman will write later.
Chap 2D.8: Epilogue
1: Future perspective | Dr. Pasman |  | Author Assigned |  | This chapter Dr. Pasman will write later.